## draft
LIST!A1 |  | Project Name:
Project Manager:
Project Engineer:
Project Code:
Filing date:
|  |  | Qty | Rate
|  | Control centre full |  | 2 | 0
|  | Control centre simple |  | 1 | 0
|  | Remote site full |  | 1 | 0
|  | Remote site simple |  | 0.5 | 0
|  | Qty of sites | 0 |  | 0
|  | Qty of sensor's types | 5
[5 empty] | Tender preparation |  | Implementation
|  | Work description | Work-time base (m/d) | Work-time per system (m/d) | Qty | Work-time (m/d) | Qty | Work-time (m/d) | Notes
|  | System design, including: |  |  |  | 0 |  | 0
| 1 | Radar performance calculation (per sensor) | 0.5 | 0.5 |  | 0 |  | 0
| 2 | VHF/AIS performance calculation Global Mapper (per sensor) | 0.5 | 0.5 |  | 0 |  | 0
| 3 | CCTV performance calculation | 0.5 | 0.5 |  | 0 |  | 0
| 4 | Network performance calculation | 3 | 3 |  | 0 |  | 0
| 5 | System Technical Description | 3 | 3 |  | 0 |  | 0
| 6 | Master plan | 2 | 2 |  | 0 |  | 0
| 7 | Dataflow diagram | 3 | 3 |  | 0 |  | 0
| 8 | Telecommunication plan | 3 | 3 |  | 0 |  | 0
| 9 | Block Diagrams | 2 | 0 |  | 0 |  | 0
| 10 | Connection Layouts | 3 | 0 |  | 0 |  | 0
| 11 | Wiring Diagram (Electrical, Grounding, Surge Protectors, Radar Assembly, Junction Boxes, etc.) (per site) | 1 | 5 |  | 0 |  | 0
| 12 | Site Plan (equipment layout on site) | 3 | 0 |  | 0 |  | 0
| 13 | Design of Equipment Container (per unit) | 5 | 5 |  | 0 |  | 0 |  |  | Tender/Bid preparation Work-time budget for SBS engineers | Base (m/w) | Risks (m/w)
| 14 | Design of Mast/Tower (per unit) | 5 | 5 |  | 0 |  | 0 |  |  | Site Survey | 0 | 0
| 15 | Design of Operator Console (per unit) | 5 | 5 |  | 0 |  | 0 |  |  | System design | 0 | 0
| 16 | Installation requirements | 1 | 5 |  | 0 |  | 0
| 17 | Civil and installation work specification | 0.5 | 2.5 |  | 0 |  | 0 |  |  | Project Implementation Work-time budget for SBS engineers | Base (m/w) | Risks (m/w)
| 18 | Factory Acceptance Test procedure | 3 | 3.5 |  | 0 |  | 0 |  |  | Site Survey | 0 | 0
| 19 | Site Acceptance Test procedure | 1 | 2.5 |  | 0 |  | 0 |  |  | System design | 0 | 0
| 20 | Scope of supply | 1 | 5 |  | 0 |  | 0 |  |  | System assembling and configuration at workbench | 0 | 0
| 21 | Selection of third-party equipment and subsystems | 1 | 5 |  | 0 |  | 0 |  |  | Execution of Wartsila FAT and/or participation at suppliers FAT(s) | 0 | 0
| 22 | Maintenance Plan | 0.5 | 0 |  | 0 |  | 0 |  |  | System installation and commissioning | 0 | 0
| 23 | Compliance Matrix | 0.5 | 0 |  | 0 |  | 0 |  |  | Supervision of civil and installation works performed by subcontractors | 0 | 0
|  | Risks (30% small … 200% large scale project) |  |  | 60 |  | 30 |  |  |  | Execution of SAT/PAT | 0 | 0
[5 empty] | 190% by default | [5 empty] | VTS operators/engineers training | 0 | 0
[11 empty] | Deploy the Advanced Intelligent Maneuvering (AIM) | 0 | 0
[11 empty] | Trips estimation for SBS engineers | Qty. of engineers in the team | Qty. of team’s trips | Total qty. of trips
| 24 | Execution of Site Survey | 3 | [7 empty] | Site Survey | 1 | 1 | 1
| 25 | System assembling and configuration at workbench | [7 empty] | 0 | Assembling and configuration at workbench | 2 | 1 | 2
| 26 | Execution of Wartsila FAT and/or participation at suppliers FAT(s) | [8 empty] | Wartsila FAT and/or suppliers FAT(s) | 0 | 0 | 0
| 27 | System installation and commissioning | 15 | 0 | [5 empty] | 0 | Installation and commissioning | 2 | 1 | 2
| 28 | Supervision of civil and installation works performed by subcontractors | [8 empty] | Supervision of civil and installation works performed by subcontractors | 0 | 0 | 0
| 29 | Execution of SAT/PAT | 1 | 2 | [6 empty] | SAT/PAT | 0 | 0 | 0
| 30 | VTS operators/engineers training | 3 | 0 | [6 empty] | VTS operators/engineers training | 1 | 1 | 1
|  | Risks (30% small … 80% large scale project) |  |  | 50 |  | 30 |  |  |  | Annual Onsite Preventive Maintenance (every 12 Months) | 1 | 1 | 1
[8 empty] | Annual |  |  | Annual Maintenance Work-time budget for SBS engineers | Base (m/w) | Risks (m/w)
| 31 | Remote Preventive Maintenance: every 6 Months | 0 | [5 empty] | year(s) |  | Remote Preventive Maintenance (every 6 Months) | 0 | 0
| 32 | Onsite Preventive Maintenance: every 12 Months | 2 | [5 empty] | year(s) |  | Onsite Preventive Maintenance (every 12 Months) | 0 | 0
| 33 | Corrective maintenance | 36 | [5 empty] | year(s) |  | Corrective maintenance | 0 | 0
|  | Additional | [9 empty] | Base (m/d) | Risks (m/d) | Total (m/d) | m/w
[11 empty] | FAT | 0 | 0 | 0 | 0
[11 empty] | Installation | 0 | 0 | 0 | 0
[12 empty] | Total m/d: | 0 | 0 | 0 | ref. | ref. | ref.
|  | SHORT SPECIFICATION OF THE SYSTEM | CC full | CC simple |  | RS full |  | RS simple |  |  | Equipment | Qty | FAT, m/d | Installation, m/d | Configuration, m/d | FAT, m/d | Installation, m/d | Configuration, m/d
|  |  | 0 | 0 |  | 0 |  | 0 |  |  | Radar
[11 empty] | Terma 5000 series Single TxRx |  | 0 | 0 | 0 |  | 2.5 | 1
[11 empty] | Terma 5000 series Dual TxRx |  | 0 | 0 | 0 |  | 4 | 1
[11 empty] | Terma 2001i |  | 0 | 0 | 0 |  | 5 | 0.5
[11 empty] | Terma Service Display for 2001i |  | 0 | 0 | 0 | 0.5 | 0.4 | 0.3
[11 empty] | GEM RT0325D (upmast) |  | 0 | 0 | 0 |  | 3 | 1
[11 empty] | GEM RT0325D (downmast) |  | 0 | 0 | 0 |  | 4 | 1
[11 empty] | GEM Sentinel Series |  | 0 | 0 | 0 |  | 2 | 0.5
[11 empty] | JRC NKE-2254 9ft |  | 0 | 0 | 0 |  | 2 | 0.5
[11 empty] | ICS |  | 0 | 0 | 0 |  | 2 | 0.5
[11 empty] | BME |  | 0 | 0 | 0 |  | 1 | 0.5
[11 empty] | GEM NKE-2254 9ft |  | 0 | 0 | 0 |  | 3 | 1
[11 empty] | Any radar slave connection |  | 0 | 0 | 0 |  | 1.6
[11 empty] | Radar Processor (incl. VARP) |  | 0 | 0 | 0 | 0.5 | 0.4 | 2
[11 empty] | RPU-5 |  | 0 | 0 | 0 | 0.1 | 0.1 | 0.1
CCTV
[11 empty] | Oxalis XP40 |  | 0 | 0 | 0 | 1.5 | 1 | 0.8
[11 empty] | Oxalis Pan Tilt + any Camera+ any Housing |  | 0 | 0 | 0 | 2.5 | 1 | 0.8
[11 empty] | Silent Sentinel OPT-XXX |  | 0 | 0 | 0 | 0.5 | 1 | 0.8
AIS
[11 empty] | Elman AIS BS ABT1103 |  | 0 | 0 | 0 | 0.2 | 0.2 | 0.8
[11 empty] | Kongsberg AIS BS 610 |  | 0 | 0 | 0 | 0.2 | 0.2 | 0.8
[11 empty] | AIS Receiver |  | 0 | 0 | 0 | 0.2 | 0.2 | 0.1
RDF
[11 empty] | Rhotheta RT800/RT1000 |  | 0 | 0 | 0 |  | 0.8 | 1.5
[11 empty] | Rohde& Schwarz DDF200M |  | 0 | 0 | 0 |  | 1 | 2
[11 empty] | Existing RDF integration |  | 0 | 0 | 0 |  | 0.1 | 1.5
VHF Radio
[11 empty] | Elman RTV 1124 (BS of 3x radios) |  | 0 | 0 | 0 | 0.45 | 1 | 0.5
[11 empty] | Spectra MX 800 (BS of 3x radios) |  | 0 | 0 | 0 | 0.45 | 1 | 0.5
[11 empty] | Jotron 7000 series (BS of 3x radios) |  | 0 | 0 | 0 | 1.5 | 1 | 1
[11 empty] | JRC JRV-600 |  | 0 | 0 | 0 | 0.15 | 1 | 0.5
[11 empty] | Sailor any desk mount |  | 0 | 0 | 0 | 0.15 | 0.5 | 0.2
[11 empty] | Omnitronics Altus |  | 0 | 0 | 0 | 3 | 0.1 | 2
[11 empty] | Omnitronics IPR 100/400 |  | 0 | 0 | 0 | 1 | 0.3 | 0.2
[11 empty] | MF/HF Radio |  | 0 | 0 | 0
[11 empty] | JRC JSS-2250 |  | 0 | 0 | 0 | 2 | 2 | 1
Meteo
[11 empty] | Vaisala WXT530 Series |  | 0 | 0 | 0 | 0.5 | 1 | 0.6
[11 empty] | Vaisala PWD |  | 0 | 0 | 0 | 0.5 | 1 | 0.6
[11 empty] | Water Level Sensor |  | 0 | 0 | 0 | 0.5 | 1 | 0.6
[11 empty] | Gill MetPak |  | 0 | 0 | 0 | 0.5 | 1 | 0.6
[11 empty] | Existing Meteo station with NMEA output |  | 0 | 0 | 0 |  | 0.5 | 0.2
[11 empty] | Buoy (Wave Height Meter, Water Current Sensor) |  | 0 | 0 | 0 |  | 0.2 | 0.3
Servers
[11 empty] | VTS Server |  | 0 | 0 | 0 | 1 | 0.5 | 5
[11 empty] | Database Server |  | 0 | 0 | 0 | 1.5 | 0.5 | 1
[11 empty] | Video Management Server VMS |  | 0 | 0 | 0 | 1 | 0.2 | 0.8
[11 empty] | Recording Server |  | 0 | 0 | 0 | 1 | 0.5 | 1
[11 empty] | Sensor Server |  | 0 | 0 | 0 | 1 | 0.5 | 1
[11 empty] | Storage |  | 0 | 0 | 0 | 2.5 | 0.5 | 2
[11 empty] | Network Management Server NMS (PRTG) |  | 0 | 0 | 0 | 1 | 0.5 | 5
[11 empty] | WEB Server |  | 0 | 0 | 0 | 3 | 0.5 | 1
[11 empty] | TrAN System Controller |  | 0 | 0 | 0 | 1 | 0.5 | 0.5
[11 empty] | TrAN Client Server |  | 0 | 0 | 0 | 1 | 0.5 | 0.5
[11 empty] | Audio Server (Audio Processor with analog audio recording) |  | 0 | 0 | 0 | 2.5 | 0.5 | 1
[11 empty] | Audio Server (Audio Processor with RTP audio recording) |  | 0 | 0 | 0 | 1 | 0.5 | 0.5
[11 empty] | Radio Management Server RMS |  | 0 | 0 | 0 | 1 | 0.5 | 5
[11 empty] | Time Server |  | 0 | 0 | 0 | 0.3 | 0.2 | 1.5
[11 empty] | VMware virtual platform |  | 0 | 0 | 0 | 4 | 1 | 1
[11 empty] | AIM Server |  | 0 | 0 | 0 | 1 | 0.5 | 1
Operator WS
[11 empty] | Operator Console (Furniture) |  | 0 | 0 | 0 |  | 4
[11 empty] | ODU PC + Display |  | 0 | 0 | 0 | 0.5 | 0.5 | 0.8
[11 empty] | CCTV ODU PC + Display |  | 0 | 0 | 0 | 0.5 | 0.5 | 0.8
[11 empty] | GMDSS PC + Display |  | 0 | 0 | 0 | 0.5 | 0.5 | 1
[11 empty] | Radio Console PC + Display + Omnitronics Alto + AFI |  | 0 | 0 | 0 | 1 | 0.2 | 0.3
[11 empty] | Radio Console PC + Display + Omnitronics RediTalk |  | 0 | 0 | 0 | 1 | 0.2 | 0.3
[11 empty] | Navi-Port PC + Display |  | 0 | 0 | 0 | 0.5 | 0.5 | 0.8
[11 empty] | WEB workstation PC + Display |  | 0 | 0 | 0 | 0.2 | 0.2 | 0
[11 empty] | 3D VTS PC + Display |  | 0 | 0 | 0 | 0.5 | 0.5 | 0.8
VTS Simulator
[11 empty] | VTS Traineer PC + Display |  | 0 | 0 | 0 | 0.5 | 0.5 | 0.8
[11 empty] | Instructor PC + Display |  | 0 | 0 | 0 | 1 | 0.5 | 5
Network
[11 empty] | Switch Unmanaged |  | 0 | 0 | 0 | 0.2 | 0.8
[11 empty] | Switch Managed |  | 0 | 0 | 0 | 1 | 0.8 | 0.5
[11 empty] | Router/ L3 Switch |  | 0 | 0 | 0 | 2.5 | 0.8 | 1.5
[11 empty] | Firewall |  | 0 | 0 | 0 | 3 | 0.8 | 1.5
[11 empty] | Microwave equipment (per link) |  | 0 | 0 | 0 |  | 0.5
Rack
[11 empty] | Rack Assembly |  | 0 | 0 | 0 | 3 | 1.5 | 0.5
Power
[11 empty] | UPS Rackmount |  | 0 | 0 | 0 | 0.4 | 0.5 | 0.8
[11 empty] | DG Set |  | 0 | 0 | 0
dGPS
[11 empty] | dGPS Receiver |  | 0 | 0 | 0 | 0.2 | 0.2 | 0.3